## COA ProjPlan
DBR COA Project Tracking | [8 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 8/3/2024 |  |  |  | NEXT REPORTING DATE: |  | 2024-09-20
MILESTONE STATUS
Person icon is in this cell | NAME: | Carolyn Marquis, Project Manager |  |  | ROOF | On time
[5 empty] | SEAWALL | Critical Delays
Envelope is in this cell | EMAIL: | chesbrewco@yahoo.com |  |  | LEGAL: Arbitration | Critical Delays
[5 empty] | INDOOR AMENITIES | Critical Delays
[5 empty] | YEAR END AUDIT | Critical Delays
Phone icon is in this cell | NEXT 30 DAY PRIORITIES: Roof Seawall Garage Insurance Pooldeck Hallway AC Year End Audits Elevators 5th Floor Tomoka Windows/Doors Security Landscaping Parking Unit Access SIRS IceMachines |  |  |  | ELEVATOR MAINTENANCE | On time
[5 empty] | STORM INSURANCE | Critical Delays
[5 empty] | 5th FLOOR CEILING | Challenges
[5 empty] | TOMOKA OWNER PORTAL | Challenges
TASK | DESCRIPTION | POC/Point of Contact | DUE DATE | ACTUAL DATE | Task Detail | ESTIMATES | ACTUALS | Notes | Followup
BANKING | [8 empty] | Yes
1 | Need Sweep Account | Nathan Wade | 2024-06-01 |  | Getting Bank products on Sweep options presentation format from Vystar and Synovous |  |  | Confirm 2% increase or higher | No
2 | Coordination Needed | Dick Burke | 2024-08-01 |  | Financial Committee & Synovous Presentation |  |  |  | Yes
3 | [8 empty] | No
ROOF |  |  |  |  | Present and Next Steps |  |  |  | Yes
1 | COA Approval Needed | Board Member: | 2023-06-18 | 2023-07-10 | COA Authorized Quotes on Temp Solution | 147000 |  |  | Yes
2 | Contract - Owner Portal | Nathan Wade | 2024-05-15 | 2024-05-10 | 5th Floor contract not in portal as of 8/23 | 4700
3 | Waiting on Parts and/or Estimates from Vendor | Natasha Herndon | 2024-06-19 | 2024-06-15 | Coordinate Quotes | 1200 | 1000 |  | No
4 | COA Board Meeting Needed | Nathan Wade | 2024-07-20 | 2024-08-21 | Add Extreme Roofing Contract to Owner Portal | 0 | 550 |  | No
5 | Insurance Needed | Kimberly Thomplison | 2024-04-12 |  | Status of Pursuing Claim? | 2000000 |  |  | Yes
6 | Tomoka Resources Needed | Kimberly Thomplison | 2024-08-27
7 | [8 empty] | Yes
SEAWALL |  |  |  |  | Present and Next Steps
1 | COA Board Meeting Needed | COA | 2023-06-01 |  | Insur Atty retained | 1500000 | 1250600
2 | Funding Needed | DBR LLC | 2023-07-01 |  | Spec Assess Passed
3 | Contact Vendor - Estimate or Performance | DBR LLC | 2023-07-16 |  | Turtle nests present
4 | Referred to Legal for recommendation | COA | 2023-08-04 |  | Emerg Mot for Injunction |  |  | Denied
5 | Paid Zmax $9,000 Trap Bags 12/23 | COA | 2024-02-19 |  | No contract and no Trap Bags | Need Refund
6 | Code Hearing 1/9/24 | Carolyn Marquis | 2024-01-08 | 2024-01-09 | Many Owners Attending
7 | Code Hearing 2/14/24 | Carolyn Marquis | 2024-02-21 |  | Fast Track for fencing & trap bags
8 | Code Hearing 4/17/24 | Carolyn Marquis |  |  | Fast Track for fencing & trap bags | DBR LLC fined $1,000 per day
9 | County Code Hearing 6/17 | FWB |  |  | Orange fencing removed and remove COA from violation
10 | Paid GC Contractors $9,000 Trap Bags 6/22/24 | Renata |  |  | GC Contracters applied for permit day of 6/17 hearing; Work to begin 7/8/2024 |  |  | Owners Paid 18,000 to GC and 9,000 to Zmax
11
12
19
GARAGE |  |  |  |  | Present and Next Steps
1 | Code Hearing 1/9/24 | Carolyn Marquis | 2024-01-08 | 2024-01-09 | Many Owners Attending
2 | Code Hearing 2/14/24 | Carolyn Marquis | 2024-02-21 |  | Fast Track for Cosmetic fixes
3 | Code & attorneys with Developer meeting on site | On Site | 2024-02-15
4 | Code Hearing 4/9/24 | Carolyn Marquis | 2024-04-09 |  | Fines are put in place $1,000 daily
5 | Code Hearing 8/15/24 | Carolyn Marquis | 2024-04-09 |  | Fines are put in place $500 daily
INSURANCE POLICY |  |  |  |  | Present and Next Steps
3 | Tomoka Resources Needed | Nathan Wade | 2023-02-12 |  | New Prop&Cas Policy 750k purchased 4/30/24
4 | Tomoka Resources Needed | Nathan Wade | 2024-11-12 |  | Begin Discussions on New Prop&Cas Policy 750k purchased 4/30/24
5
6
7
8
9
POOL DECK
1 | DBR LLC Approval Needed | Developer abandonment | 2023-12-05 |  | Code Enforcement Inspections
2 | Referred to Legal for recommendation | COA Attorney | 2023-12-11 |  | COA filed Emerg Injunct denied
3 | DBR LLC Approval Needed | Developer abandonment | 2023-12-11
4 | DBR LLC Approval Needed | Developer and COA Mediation | 2024-03-28
5
Hallway AC Units |  |  |  |  | Present and Next Steps
1 | COA Approval Needed | Judy Lairabee | 2023-07-26 |  | Board was notified
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-09-01 |  | Need estimates from vendors
3 | COA Approval Needed | Kimberly Thomplison | 2023-12-28
4 | COA Board Meeting Needed | Bonnie Laslo | 2023-12-28 |  | 12/30 Bonnie Posted delivery of 13 COMPLETED | 71500
5 | Tomoka Resources Needed | Kimberly Thomplison | 2024-08-20 |  | Need hallway controls moved inside utility closet each floor
6
7
YEAR END AUDIT
1 | Tomoka Resources Needed | Nathan Wade | 2024-08-26 |  | Need accountant per contract for 2021 and 2022
2 | COA Board Meeting Needed | Nathan Wade | 2023-12-30 |  | Lawsuit filed/Owners requested next steps
3 | Tomoka Resources Needed | Bonnie Laslo | 2024-01-03 |  | Bonnie posted complete by end of Jan
4 | Other Needed | Bonnie Laslo | 2024-02-27 |  | Firm hired and paid $4,000 to do 21,22,23
5 | COA Approval Needed | Bonnie Laslo | 2024-04-04 |  | Update Promised at Board Meeting
6 | Long term reconciliation needed | Dick Burke & Nathan Wade | 2024-06-18 |  | CPA hired; stopped due to missing Jan 2021 Bank Statement $$
7 | COA Approval Needed | Renata | 2024-08-20 |  | Requested solution added for vote to BOD 8/29 Meeting
8
9
ELEVATORS |  |  |  |  | Present and Next Steps
1 | Professional Deisgn Resources Needed | COA | 2024-07-23 |  | Bid packages went out and designs submitted to elevator consultant | 1500000
2 | Coordination Needed | Judy Lairabee | 2024-08-26 |  | Modernization Recommended by vendor
3 | Elevator clutches fixed | Bonnie FB Post | 2023-12-28 |  | Modernization in process
4 | Elevator repairs in progress | Bonnie FB Post | 2023-12-28 |  | Modernization in process
5 | SA for Seawall 1 million moved to Elevators | Board FB Post | 2024-02-11 |  | Modernization in process
6 | SA for Seawall 1 million moved to Elevators | Board FB Post | 2024-04-04 |  | Modernization in process
7 | Tomoka Resources Needed | Nathan Wade | 2024-07-05 |  | Elevator bids, contracts are missing from portal
PIGEON & PEST |  |  |  |  | Present and Next Steps
1 | Waiting on Parts and/or Estimates from Vendor | Judy Lairabee | 2023-09-01 |  | Estimate forwarded to COA | 80000
2
3
5th Floor Ceiling |  |  |  |  | Present and Next Steps
1 | COA Approval Needed |  | 2023-05-12 |  | Get Estimates after calls | 4700
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-08-14 |  | Have vendor fix | 4700
3 | Tomoka Resources Needed | Kimberly Thomplison | 2023-11-16 |  | Need vendor Extreme Roofing to return & fix
4 | Tomoka Resources Needed | Kimberly Thomplison | 2024-03-01 |  | Bonnie posted a new temporary roof install would include 5th floor fix??? FB | 22000
5 | Tomoka Resources Needed | Kimberly Thomplison | 2024-05-24 |  | Kimberly is working with Extreme Roof to begin work on 8/20/24 | 45000
6
7
CAM Resources Management |  |  |  |  | Present and Next Steps
1 | Tomoka Resources Needed | Nathan Wade | 2023-05-17 |  | Owner Request Made per statute to update
2 | Tomoka Resources Needed | Nathan Wade | 2023-06-15 |  | Owner Request Made per statute to update
3 | Tomoka Resources Needed | Nathan Wade | 8/28/203 |  | Owner Request Made per statute to update
4 | Tomoka Resources Needed | Nathan Wade | 2023-09-15 |  | Owner Request Made per statute to update
5 | CAM development in-house | Unsure | 2024-03-01 |  | Current Contract expires 9/30/24
6 | COA Approval Needed | Patrick O'Donnel | 2024-06-17 |  | Board President suggests performance measures for new contract 24-25
7 | Maintenance & Vendor Committee | Carolyn Marquis | 2024-08-12 |  | Committee reviewed contract, put feedback together so did Renata and forwarded to Tomoka
8 | Coordination Needed | Nathan Wade | 2024-08-14 |  | Requested Tomoka availability to negotiate and Nathan setting meeting by 9/1/2024
9
10
Communication Plan |  |  |  |  | Present and Next Steps
1 | Committees Setup | Carolyn Marquis | 2023-12-05 |  | Have volunteers; Need Board Approval
2 | Owner Portal Audit | Carolyn Marquis | 2024-06-08 |  | Completed
3 | Floor Captains | Carolyn Marquis | 2023-12-28 |  | Onsite Meeting & Tour
4 | Social Activity Needed | Carolyn Marquis | 2024-01-19 |  | Big Tuna Monthly Meet&Mingle Candidates Running 2024
5 | COA Approval Needed | COA Board | 2024-07-30 |  | Board approves Committees
6 | Communication Committee first meeting | Carolyn Marquis | 2024-08-05 |  | Discussion on purpose, upcoming key events and dates, how to reach all owners.
7 | COA Approval Needed | COA Board | 2024-08-20 |  | Minutes, Newsletter and Committee purpose submitted to BOD for 8/29/ Mtg approval
8
Windows/Doors
1 | COA Approval Needed | Rober Kubly | 2023-12-11 |  | Windows and Doors being fixed | 64000
2 | COA Approval Needed | Bonnie Laslo | 2023-12-28 |  | FB List that Windows & Doors in progress
3 | COA Approval Needed | Kimberly Thomplison | 2024-02-01 |  | Board Mtg Update 3 more windows done
4 | Tomoka Resources Needed | Kimberly Thomplison | 2024-02-18 |  | Roger continues to meet with Kimberly but many windows and doors are special order. We need better organization and prioritization.
5 | COA Approval Needed | Kimberly Thomplison | 2024-04-01 |  | Update Promised at 4/4/24 Board Meeting
6 | Tomoka Resources Needed | Kimberly Thomplison | 2024-06-11 |  | Need to scrub portal list against Omega Glass list | 40000
7
Property Security
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Need additional Security with homeless in Bldg
2 | COA Approval Needed | DBR Board | 2024-02-14 |  | Requested additional security and ignored
3 | COA Approval Needed | DBR Board | 2024-02-27 |  | Late notification Bike Week multiple tows and altercations - Bike Week Kim off Sat/Sun and left early Mon plus off Tues & Wed; Many towed
4 | COA Approval Needed | DBR Board | 2024-04-04 |  | Board increased Budget for Security from 10 to 12 hours with increased regular assessment to 733 monthly but no 24/7 security has been put in place as of 4/16 NEED CONTRACT IN PORTAL
5 | Tomoka Resources Needed | Kimberly Thomplison | 2024-06-27 |  | Kimberly is out for long weekend Thurs-Sun and we need Tomoka to provide onsite backup
6 | Tomoka Resources Needed | Kimberly Thomplison | 2024-08-09 |  | Need to plan coverage for holidays with security
7 | COA Approval Needed | DBR Board | 2024-08-22 |  | Approval needed for additional security submitted
8
Landscaping
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Roger requested Board act on quotes given
2 | Social Activity Needed | Roger Kubly | 2024-02-10 |  | Angie Russel and Donna Kinnett coordinated a mulch party
3 | Social Activity Needed | Roger Kubly | 2024-02-16 |  | Roger Kubly and Dave Marquis coordinated a mulch Party
4 | COA Approval Needed | Bonnie Lalso | 2024-04-04 |  | Broke out line items on budget approved
5 | Tomoka Resources Needed | Kimberly Thomlinson | 2024-08-11 |  | Get all inclusive quotes for palm trees in front and fraun removals
Parking Lease
1 | Coordination Needed | Bonnie Lalso | 2023-12-16 |  | FB announced contract extended until 6/30/24
2 | COA Approval Needed | Roger Kubly | 2024-03-01 |  | Checking with Dennys for back area?
3 | COA Approval Needed | Carolyn Marquis | 2024-03-01 |  | Checking with Alfred on Tshirt price?
4 | COA Approval Needed | Renata | 2024-03-01 |  | Lease extended through Sept 30, 2024; NEED LEASE IN PORTAL
5 | COA Approval Needed | Patrick | 2024-08-13 |  | Requested to discuss with owner
6
7
8
Legal Resources Management
1 | Magistrate Hearing 1 | Legal Committee | 2024-01-09 |  | 22Owners/71online - 30 days for trap bags and fence and fines will begin
2 | Magistrate Hearing 2 | Legal Committee | 2024-02-14 |  | H wants walk garage walkthrough, Magistrate finds H as owner; 30 days then fines
3 | Magistrate Hearing 3 | Legal Committee | 2024-03-01 |  | Hearing on Garage and Balconies
3 | Mediation #3 | Board | 2024-03-28 |  | Demonized NDA; nothing shared. Details worked next 30 days - Maybe share with owners?
4 | Magistrate Hearing 3 | Legal Committee | 2024-04-09 |  | Fines to H 1,000daily. Trap bags and fence order
5 | Mediation #4 | Board | 2024-04-11 |  | Details were to be worked out; by 4/22 nothing to share with owners; additional mtg #5 6/27
6 | Volusia Circuit Court Hearing on 14th Floor | Joel Attorney | 2024-04-23 |  | Procedural Motions Hearing
7 | Volusia Circuit Court Marquis vs. COA | Joel Attorney | 2024-05-09 |  | Both Parties Agree Dismissal except COA entered $13,000 in attorney fee award
8 | Magistrate Hearing 4 | Legal Committee | 2024-06-05 |  | Garage Hearing Fine Assessed $1,000 per day
9 | County Code Hearing 6/17 Seawall | Board | 2024-06-28 |  | Had to remove COA from Case
10 | Lawfirm Engagement Contract? | Legal Committee | 2024-01-01 |  | NEED CONTRACT IN PORTAL; requested multiple times
11 | Mediation #6 | Board | 2024-07-05 |  | Details were to be worked out; by 7/15 nothing to share with owners; Need Plate survey
12 | Mediation #7 | Board | 2024-07-12 |  | Everything remain unanswered: Need Plate survey
13 | Mediation #8 | Board | 2024-08-18 |  | Sun. 9am Discrepancy with submitted property Survey and invoice for same
14
15
UNIT ACCESS
1 | Coordination Needed | Kimberly Thomplison | 2024-06-25 |  | We need to scrub owner list of access on every room and verify ; Carolyn Marquis has agreed to assist
2 | Maintenance & Vendor Committee | kimberly Thomplison | 2024-08-20 |  | Carolyn and Kimberly Meeting to go over list and draft mailer
3
4
5
STORM INSURANCE |  |  |  |  | Present and Next Steps
1 | Insurance Needed | Hire the Insurance Adjuster Attorney for COA | 2023-01-05 |  | Board has refused to hire expert
2 | Referred to Legal for recommendation | COA Attorney | 2023-01-11 |  | Board continues to do nothing on Insurance
3 | COA Approval Needed | Nathan Wade | 2023-02-12 |  | Need Public Adjuster hired; but we are named insured and Developer owns policy
4
5
6
7
FirePump Proposal |  |  |  |  | Present and Next Steps
1 | S.A.F.E. | Kimberly Thomplison | 2024-06-28 |  | Proposal sent to Kim; need two additional?
2
3
4
5
6
7
STRUCTURAL RESERVE STUDY
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Was introduced as priority for 2024 at Board mtg
2 | COA Approval Needed | DBR Board | 2024-02-14 |  | Patrick requested Nathan get quotes for same
3 | COA Approval Needed | DBR Board | 2024-05-05 |  | Nath forwards 1 quote from 2/27/2024 that has expired
4 | COA Approval Needed | DBR Board | 2024-06-17 |  | Nathan forwards 3 quotes 6/5/24 for SIRS; Board agreed and had someone on property 6/19
5 | Tomoka Resources Needed | Nathan Wade | 2024-07-28 |  | Carolyn requested results; Nathan said 1-2 months
6 | Tomoka Resources Needed | Nathan Wade | 2024-08-13 |  | 8/22 Second inspection scheduled on property
7
8
Ice Machines |  |  |  |  | Present and Next Steps
1 | Vendor Quotes Needed | Kimberly Thomplison | 2024-06-28 |  | Need estimates for commercial ice machines CM called Pioneer Appliance, American Appliance, Allens Appliance Service, Mark Appliance & Refrigerator Repair | Mark Appliance is $59.00 to diagnose that can be applied to overall costs if you go with his proposal
2 | Maintenance & Vendor Committee | Carolyn Marquis | 2024-08-12 |  | Committee is collecting quotes
3
4
5
6
7

## Rule&Fine
DBR Rules & Fines | [5 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 8/3/2024 |  |  | NEXT REPORTING DATE:
Person icon is in this cell | Dave Hirosky
CHAIRPERSON | Christianne Nahkla
RENATA GOZDZIAK | Billy Martin
Frank Scaggs
CATEGORIES | INCIDENT | FEE | CAM NOT 1 | CAM NOT 2 | CURRENT BALANCE | Followup
UNIT 465 | [5 empty] | Yes
1 | [5 empty] | No
2
3 | [5 empty] | No
UNIT 1211 | [5 empty] | Yes
1 |  | 2023-06-18 | 2023-07-10 |  | 2000 | Yes
2 |  | 2024-05-15 | 2024-05-10
3 |  | 2024-06-19 | 2024-06-15 |  | 1000 | No

## Finance
DBR FINANCE | [5 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 8/23/2024 |  |  | NEXT REPORTING DATE:
| MEMBERS |  |  | Sub Team Members
Person icon is in this cell
CHAIRPERSON
DICK BURKE
CATEGORIES | INCIDENT | FEE | CAM NOT 1 | CAM NOT 2 | CURRENT BALANCE | Followup
JULY MONTHLY STATEMENT | [5 empty] | Yes
1 | [5 empty] | No
2
3 | [5 empty] | No
AUDITOR | [5 empty] | Yes
1 |  | 2023-06-18 | 2023-07-10 |  | 2000 | Yes
2 |  | 2024-05-15 | 2024-05-10
3 |  | 2024-06-19 | 2024-06-15 |  | 1000 | No

## Communication
DBR COMMUNICATION | [5 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 8/23/2024 |  |  | NEXT REPORTING DATE: |  | 2024-09-20
Person icon is in this cell | Karen Fanning
CHAIRPERSON | Peggy Defiglio
CAROLYN MARQUIS | Angie Thuli
Connie Vanhouten
Mary Turman
DATE | STATUS | DATE | APPROVED | TASK OWNER | COST | Followup
Newsletter | [5 empty] | Yes
1 | Submitted for BOD Approval | 2024-08-20 |  | Carolyn |  | No
2
3 | [5 empty] | No
Yes
1 |  | 2023-06-18 | 2023-07-10 |  | 2000 | Yes
2 |  | 2024-05-15 | 2024-05-10
3 |  | 2024-06-19 | 2024-06-15 |  | 1000 | No

## Main&Vendor
DBR Maintenance & Vendor | [5 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 8/23/2024 |  |  | NEXT REPORTING DATE: |  | 2024-09-20
Person icon is in this cell | Roger Kubly
CHAIRPERSON | David Marquis
CAROLYN MARQUIS | Rob Maladono
Greg Cole
Lisa Baxter
DATE | STATUS | DATE | APPROVED | TASK OWNER | COST | Followup
M request form | [5 empty] | Yes
1 | Submitted for BOD Approval | 2024-08-20 |  | Carolyn |  | No
2
3 | [5 empty] | No
Palm Trees | [5 empty] | Yes
1 | Submitted to Kimberly | 2024-08-12 | 2024-06-29 | Roger | 2000 | Yes
2 |  | 2024-05-15 | 2024-05-10
3 |  | 2024-06-19 | 2024-06-15 |  |  | No
Ice Machines | [5 empty] | Yes
1 | Lisa Baxter Researching | 2024-08-05 |  | Lisa | 2000 | Yes
2 |  | 2024-05-15 | 2024-05-10
3 |  | 2024-06-19 | 2024-06-15 |  |  | No
Security Firms | [5 empty] | Yes
1 | Submitted to Kimberly | 2024-08-18 | 2024-06-29 | Carolyn | 17000 | Yes
2 |  |  | 2024-05-10
3 |  |  | 2024-06-15
Tomoka Contract
1 | Submitted to Nathan Wade for review | 2024-08-15 |  |  | 168000 | Yes
2 | Scheduling a meeting to negotiate | 2024-08-22
3

## Floor Capt
FLOOR AT DBR | NAMES | NUMBER
1 | Carolyn and David Marquis | 240 298-1195
2
3 | Mary and Larry Thurman | 386 301-0963
4 | Karen Fanning | 502 296-4636
5 | Ricky and Susan / Sammy & Tracy | 813 246-0046
6 | Linda Turkowski/ Mae | 608 931-9486
7 | Roger and Martha Kubly | 608 628-2068
8
9
10 | Jill and Joe | 386 843-3194
11
12 | Vita and Allen
13
14
Kimberly Thomplison |  | 386 463-0204
Tomoka Property |  | 386 387-2010
Security

## Resource
Resource Needed
Click on the Resources description to update the project plant for the Description type and hit 'enter'
Resources Needed
COA Approval Needed
DBR LLC Approval Needed
Vendor Quotes Needed
Tomoka Resources Needed
Insurance Needed
Coordination Needed
Funding Needed
Waiting on Parts and/or Estimates from Vendor
Referred to Legal for recommendation
Law Enforcement Needed
Governmental Expertise Needed
Social Activity Needed
Other Needed