## COA ProjPlan
DBR COA Project Tracking | [8 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 1/3/2024 |  |  |  | NEXT REPORTING DATE: |  | 2024-02-26
MILESTONE STATUS
Person icon is in this cell | NAME: | Carolyn Marquis, Project Manager |  |  | ROOF | On time
[5 empty] | SEAWALL | Critical Delays
Envelope is in this cell | EMAIL: | chesbrewco@yahoo.com |  |  | SECURITY | Challenges
[5 empty] | INDOOR AMENITIES | Critical Delays
[5 empty] | YEAR END AUDIT | Critical Delays
Phone icon is in this cell | PHONE: | 443 783-5705 |  |  | ELEVATOR MAINTENANCE | On time
[5 empty] | PIGEONS | Challenges
[5 empty] | 5th FLOOR CEILING | Challenges
[5 empty] | TOMOKA OWNER PORTAL | Critical Delays
TASK | DESCRIPTION | POC/Point of Contact | DUE DATE | ACTUAL DATE | Task Detail | Estimated price | TOTALS RAISED | Notes | Photo
BANKING | [8 empty] | Yes
1 | Vendor Quotes Needed | David Marquis | 2024-02-01 |  | Collecting banking information on Condo Products now |  |  | capitalproductions@yahoo.com | Yes
2
3 | [8 empty] | No
ROOF |  |  |  |  | Present and Next Steps |  |  |  | Yes
1 | COA Approval Needed | Board Member: | 2023-09-27 | 2024-01-27 | COA Authorized Quotes on Temp Solution | 47000 | 55000 | capitalproductions@yahoo.com | Yes
2 | Contract - Owner Portal | Judy | 2023-10-29 | Incomplete
3 | Waiting on Parts and/or Estimates from Vendor | Natasha | 2023-12-03 | 2023-11-29 | Coordinate Quotes | 1200 | 1000 |  | No
4 | COA Board Meeting Needed | Nathan Wade | 2024-01-03 | 2024-02-04 | Add Extreme Roofing Contract to Owner Portal | 0 | 550 |  | No
5 | Tomoka Resources Needed | Kimberly Thomplison | 2024-02-09 |  | Status Insurance that Roofing Company Pursing? |  |  |  | No
SEAWALL |  |  |  |  | Present and Next Steps
1 | COA Board Meeting Needed | COA | 2023-06-01 |  | Insur Atty retained | 1500000 | 1250600
2 | Funding Needed | DBR LLC | 2023-07-01 |  | Spec Assess Passed
3 | Contact Vendor - Estimate or Performance | DBR LLC | 2023-07-16 |  | Turtle nests present
4 | Referred to Legal for recommendation | COA | 2023-08-04 |  | Emerg Mot for Injunction |  |  | Denied
5 | Code Hearing 1/9/24 | Carolyn Marquis | 2024-01-08 | 2024-01-09 | Many Owners Attending
6
7
5 | Governmental Expertise Needed | Volusia County | 2024-03-07 | 2024-01-07 | Get Clarification |  |  |  | Yes
POOL DECK |  |  |  |  | Present and Next Steps
1 | DBR LLC Approval Needed | Developer abandonment | 2023-12-05 |  | Code Enforcement Inspections
2 | Referred to Legal for recommendation | COA Attorney | 2023-12-11 |  | COA filed Emerg Injunct denied
3
Hallway AC Units |  |  |  |  | Present and Next Steps
1 | COA Approval Needed | Judy Lairabee | 2023-07-26 |  | Board was notified |  |  | jlairabee@tomokapm.com
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-09-01 |  | Need estimates from vendors |  |  | jlairabee@tomokapm.com
3 | COA Approval Needed | Kimberly Thomplison | 2023-12-28
4 | COA Board Meeting Needed | Bonnie Laslo | 2023-12-28 |  | 12/30 Bonnie Posted delivery of 13 | 71500
YEAR END AUDIT |  |  |  |  | Present and Next Steps
1 | Tomoka Resources Needed | Nathan Wade | 2024-02-09 |  | Need accountant per contract for 2021 and 2022
2 | COA Board Meeting Needed | Nathan Wade | 2023-12-30 |  | Lawsuit filed/Owners requested next steps
3
ELEVATOR MAINTENANCE |  |  |  |  | Present and Next Steps
1 | Professional Deisgn Resources Needed | COA | 2024-01-06 |  |  | 1500000
2 | Coordination Needed | Judy Lairabee | 2024-02-09 |  | Modernization Recommended by vendor
3 | Elevator clutches fixed | Bonnie FB Post | 2023-12-28
4 | Elevator repairs in progress | Bonnie FB Post | 2023-12-28
5
UTILITIES TRACKING |  |  |  |  | Present and Next Steps
1 | Pull water monthly data fro last 12 months. | Roger Kubly | 2024-05-09 |  |  | 1500000
2 | Coordination Needed | Kimberly Thomplison | 2024-05-09 |  | Modernization Recommended by vendor
3 | Schedule Unit Checks | Kimberly Thomplison | 2023-04-28
4
6
7
PIGEON & PEST |  |  |  |  | Present and Next Steps
1 | Waiting on Parts and/or Estimates from Vendor | Judy Lairabee | 2023-09-01 |  | Estimate forwarded to COA | 80000
2
3
5th Floor Ceiling |  |  |  |  | Present and Next Steps
1 | COA Approval Needed |  | 2023-05-12 |  | Get Estimates after calls | 4700 |  | capitalproductions@yahoo.com
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-08-14 |  | Have vendor fix | 1200 |  | jlairabee@tomokapm.com
3 | Tomoka Resources Needed | Kimberly Thomplison | 2023-11-16 |  | Need vendor Extreme Roofing to return & fix
4
5
Tomoka Owner Portal |  |  |  |  | Present and Next Steps
1 | Tomoka Resources Needed | Nathan Wade | 2023-05-17 |  | Owner Request Made per statute to update
2 | Tomoka Resources Needed | Nathan Wade | 2023-06-15 |  | Owner Request Made per statute to update
3 | Tomoka Resources Needed | Nathan Wade | 8/28/203 |  | Owner Request Made per statute to update
4 | Tomoka Resources Needed | Nathan Wade | 2023-09-15 |  | Owner Request Made per statute to update
5
6
Communication Plan |  |  |  |  | Present and Next Steps
1 | Membership Items | Roger Kubly | 2023-12-05 |  | Developing List to Review with Team
2 | Newsletter by email | Carolyn Marquis | 2024-01-08 |  | In draft form slated for deliver 1/31/24
3 | Floor Captains | Carolyn Marquis | 2023-12-28 |  | Onsite Meeting & Tour
4 | Social Activity Needed | Carolyn Marquis | 2024-01-01 |  | Big Tuna Meet&Mingle Candidates Running 2024 Scheduled 1/19/24
5 | DBR Workshops | Dick Burke | 2024-01-24 |  | Developing Consultant Consortium
6 | Website Design | Dick Burke | 2024-01-20 |  | In design and planning phase
Windows/Doors
1 | COA Approval Needed | Rober Kubly | 2023-12-11 |  | Windows and Doors being fixed | 64000
2 | COA Approval Needed | Bonnie Laslo | 2023-12-28 |  | FB List that Windows & Doors in progress
3
4
Property Security
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Need additional Security with homeless in Bldg
2
3
4
Landscaping
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Roger requested Board act on quotes given
2
3
4
Parking Lease
1 | Coordination Needed | Bonnie Lalso | 2023-12-16 |  | FB announced contract extended until 6/30/24
2
3
4
Contractual Reviews
1 | Coordination Needed | Legal
2 |  | CAM
3 |  | Cleaning
4 |  | Security
Bylaws Review
1 | Coordination Needed
2
3
4
[5 empty] | TOTALS | 4769600 | 1307150

## 20 hours Availability
On Site Days | In | out | total | Employee Initials
2023-08-28 | 9:30 | 1:30 | 4 | Had doctors appointment
2023-08-29 | 9
2023-08-30 | 9
2023-09-04
2023-09-05
2023-09-06
2023-09-11
2023-09-12
2023-09-13
2023-09-18
2023-09-19
2023-09-20
2023-09-25
2023-09-26
2023-09-27

## Descriptions
Description Options
Click on the Resources description to update the project plant for the Description type and hit 'enter'
Resources Needed
COA Approval Needed
DBR LLC Approval Needed
Vendor Quotes Needed
Tomoka Resources Needed
Insurance Needed
Coordination Needed
Funding Needed
Waiting on Parts and/or Estimates from Vendor
Referred to Legal for recommendation
Law Enforcement Needed
Governmental Expertise Needed
Social Activity Needed
Other Needed