## COA ProjPlan
DBR COA Project Tracking | [8 empty] | House icon is in this cell
PROJECT PLAN LAST UPDATED: 4/16/2024 |  |  |  | NEXT REPORTING DATE: |  | 2024-05-17
MILESTONE STATUS
Person icon is in this cell | NAME: | Carolyn Marquis, Project Manager |  |  | ROOF | On time
[5 empty] | SEAWALL | Critical Delays
Envelope is in this cell | EMAIL: | chesbrewco@yahoo.com |  |  | LEGAL: Arbitration | Critical Delays
[5 empty] | INDOOR AMENITIES | Critical Delays
[5 empty] | YEAR END AUDIT | Critical Delays
Phone icon is in this cell | PHONE: | 443 783-5705 |  |  | ELEVATOR MAINTENANCE | On time
[5 empty] | INSURANCE | Critical Delays
[5 empty] | 5th FLOOR CEILING | Challenges
[5 empty] | TOMOKA OWNER PORTAL | Critical Delays
TASK | DESCRIPTION | POC/Point of Contact | DUE DATE | ACTUAL DATE | Task Detail | Estimated price | TOTALS RAISED | Notes | Photo
BANKING | [8 empty] | Yes
1 | Vendor Quotes Needed | David Marquis | 2024-02-01 |  | Getting Bank products in presentation format from Vystar and Synovous |  |  | capitalproductions@yahoo.com | Yes
2
3 | [8 empty] | No
ROOF |  |  |  |  | Present and Next Steps |  |  |  | Yes
1 | COA Approval Needed | Board Member: | 2023-12-12 | 2024-04-12 | COA Authorized Quotes on Temp Solution | 47000 | 55000 | capitalproductions@yahoo.com | Yes
2 | Contract - Owner Portal | Nathan Wade | 2024-01-13 | Incomplete
3 | Waiting on Parts and/or Estimates from Vendor | Natasha Herndon | 2024-02-17 | 2024-02-13 | Coordinate Quotes | 1200 | 1000 |  | No
4 | COA Board Meeting Needed | Nathan Wade | 2024-03-19 | 2024-04-20 | Add Extreme Roofing Contract to Owner Portal | 0 | 550 |  | No
5 | Tomoka Resources Needed | Kimberly Thomplison | 2024-04-25 |  | Status Insurance that Roofing Company Pursing? |  |  |  | No
SEAWALL |  |  |  |  | Present and Next Steps
1 | COA Board Meeting Needed | COA | 2023-06-01 |  | Insur Atty retained | 1500000 | 1250600
2 | Funding Needed | DBR LLC | 2023-07-01 |  | Spec Assess Passed
3 | Contact Vendor - Estimate or Performance | DBR LLC | 2023-07-16 |  | Turtle nests present
4 | Referred to Legal for recommendation | COA | 2023-08-04 |  | Emerg Mot for Injunction |  |  | Denied
5 | Code Hearing 1/9/24 | Carolyn Marquis | 2024-01-08 | 2024-01-09 | Many Owners Attending
6 | Code Hearing 2/14/24 | Carolyn Marquis | 2024-02-21 |  | Fast Track for fencing & trap bags
7 | Code Hearing 4/9/24 | Carolyn Marquis |  |  | Fast Track for fencing & trap bags
GARAGE |  |  |  |  | Present and Next Steps
1 | Code Hearing 1/9/24 | Carolyn Marquis | 2024-01-08 | 2024-01-09 | Many Owners Attending
2 | Code Hearing 2/14/24 | Carolyn Marquis | 2024-02-21 |  | Fast Track for Cosmetic fixes
3 | Code & attorneys with Developer meeting on site | On Site | 2024-02-15 |  | GARAGE FIXES WALK THROUGH
4 | Code Hearing 4/9/24 | Carolyn Marquis
5
INSURANCE |  |  |  |  | Present and Next Steps
1 | Insurance Needed | Hire the Insurance Adjuster Attorney for COA | 2023-01-05 |  | Board has refused to hire expert
2 | Referred to Legal for recommendation | COA Attorney | 2023-01-11 |  | Board continues to do nothing on Insurance
3 | Tomoka Resources Needed | Nathan Wade | 2023-02-12 |  | Nothing being done by Board
4
5
6
7 | Governmental Expertise Needed | Volusia County | 2024-05-22 | 2024-03-23 | Get Clarification |  |  |  | Yes
POOL DECK
1 | DBR LLC Approval Needed | Developer abandonment | 2023-12-05 |  | Code Enforcement Inspections
2 | Referred to Legal for recommendation | COA Attorney | 2023-12-11 |  | COA filed Emerg Injunct denied
3 | DBR LLC Approval Needed | Developer abandonment | 2023-12-11 |  | Board paid $9,000 for trap bags but no install scheduled 4/3 code hearing
4 | DBR LLC Approval Needed | Developer and COA Mediation | 2024-03-28
5
Hallway AC Units |  |  |  |  | Present and Next Steps
1 | COA Approval Needed | Judy Lairabee | 2023-07-26 |  | Board was notified
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-09-01 |  | Need estimates from vendors
3 | COA Approval Needed | Kimberly Thomplison | 2023-12-28
4 | COA Board Meeting Needed | Bonnie Laslo | 2023-12-28 |  | 12/30 Bonnie Posted delivery of 13 | 71500
5
6
7
YEAR END AUDIT
1 | Tomoka Resources Needed | Nathan Wade | 2024-04-25 |  | Need accountant per contract for 2021 and 2022
2 | COA Board Meeting Needed | Nathan Wade | 2023-12-30 |  | Lawsuit filed/Owners requested next steps
3 | Tomoka Resources Needed | Bonnie Laslo | 2024-01-03 |  | Bonnie posted complete by end of Jan
4 | Other Needed | Bonnie Laslo | 2024-02-27 |  | Firm hired and paid $4,000 to do 21,22,23
5 | COA Approval Needed | Bonnie Laslo | 2024-04-04 |  | Update Promised at Board Meeting
6
ELEVATORS |  |  |  |  | Present and Next Steps
1 | Professional Deisgn Resources Needed | COA | 2024-03-22 |  | Bid packages went out and designs submitted to elevator consultant | 1500000
2 | Coordination Needed | Judy Lairabee | 2024-04-25 |  | Modernization Recommended by vendor
3 | Elevator clutches fixed | Bonnie FB Post | 2023-12-28
4 | Elevator repairs in progress | Bonnie FB Post | 2023-12-28
5 | SA for Seawall 1 million moved to Elevators | Board FB Post | 2024-02-11
6 | SA for Seawall 1 million moved to Elevators | Board FB Post | 2024-04-04
7
PIGEON & PEST |  |  |  |  | Present and Next Steps
1 | Waiting on Parts and/or Estimates from Vendor | Judy Lairabee | 2023-09-01 |  | Estimate forwarded to COA | 80000
2
3
5th Floor Ceiling |  |  |  |  | Present and Next Steps
1 | COA Approval Needed |  | 2023-05-12 |  | Get Estimates after calls | 4700
2 | Contact Vendor - Estimate or Performance | Judy Lairabee | 2023-08-14 |  | Have vendor fix | 1200
3 | Tomoka Resources Needed | Kimberly Thomplison | 2023-11-16 |  | Need vendor Extreme Roofing to return & fix
4 | Tomoka Resources Needed | Kimberly Thomplison | 2024-03-01 |  | Bonnie posted a new temporary roof install is ready??? FB
5
6
7
CAM Resources Management |  |  |  |  | Present and Next Steps
1 | Tomoka Resources Needed | Nathan Wade | 2023-05-17 |  | Owner Request Made per statute to update
2 | Tomoka Resources Needed | Nathan Wade | 2023-06-15 |  | Owner Request Made per statute to update
3 | Tomoka Resources Needed | Nathan Wade | 8/28/203 |  | Owner Request Made per statute to update
4 | Tomoka Resources Needed | Nathan Wade | 2023-09-15 |  | Owner Request Made per statute to update
5 | CAM development in-house | Unsure | 2024-03-01 |  | Suggestion to Explore from Dick Burke
6
7
Communication Plan |  |  |  |  | Present and Next Steps
1 | Coordination Needed | Roger Kubly | 2023-12-05
2 | Newsletter by email | Carolyn Marquis | 2024-01-08 |  | Completed
3 | Floor Captains | Carolyn Marquis | 2023-12-28 |  | Onsite Meeting & Tour
4 | Social Activity Needed | Carolyn Marquis | 2024-01-19 |  | Big Tuna Meet&Mingle Candidates Running 2024
5 | Consultant Consortium | Dick Burke | 2024-01-22 |  | Analysis of Visioning Surveys
6 | Coordination Needed | COA Board | 2024-03-02 |  | Communication Breakdown whenParking Policy from DBR II not communicated to owners many towed Bike Week
7 | Election Voting | CAM Nathan Wade | 2024-04-16 |  | No ballots received deadline is 4/19
8
Windows/Doors
1 | COA Approval Needed | Rober Kubly | 2023-12-11 |  | Windows and Doors being fixed | 64000
2 | COA Approval Needed | Bonnie Laslo | 2023-12-28 |  | FB List that Windows & Doors in progress
3 | COA Approval Needed | Kimberly Thomplison | 2024-02-01 |  | Board Mtg Update 3 more windows done
4 | Tomoka Resources Needed | Kimberly Thomplison | 2024-02-18 |  | Roger continues to meet with Kimberly but many windows and doors are special order. We need better organization and prioritization.
5 | COA Approval Needed | Kimberly Thomplison |  |  | Update Promised at 4/4/24 Board Meeting
6
7
Property Security
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Need additional Security with homeless in Bldg
2 | COA Approval Needed | DBR Board | 2024-02-14 |  | Requested additional security and ignored
3 | COA Approval Needed | DBR Board | 2024-02-27 |  | Late notification Bike Week multiple tows and altercations - Bike Week Kim off Sat/Sun and left early Mon plus off Tues & Wed
4 | COA Approval Needed | DBR Board | 2024-04-04 |  | Board increased Budget for Security from 10 to 12 hours with increased regular assessment to 733 monthly but no 24/7 security has been put in place as of 4/16
5
Landscaping
1 | COA Approval Needed | Kimberly Thomplison | 2023-12-16 |  | Roger requested Board act on quotes given
2 | Social Activity Needed | Roger Kubly | 2024-02-10 |  | Angie Russel and Donna Kinnett coordinated a mulch party
3 | Social Activity Needed | Roger Kubly | 2024-02-16 |  | Roger Kubly and Dave Marquis coordinated a mulch Party
4 | COA Approval Needed | Bonnie Lalso | 2024-04-04 |  | Broke out line items on budget approved
5
Parking Lease
1 | Coordination Needed | Bonnie Lalso | 2023-12-16 |  | FB announced contract extended until 6/30/24
2 | COA Approval Needed | Roger Kubly | 2024-03-01 |  | Checking with Dennys for back area
3 | COA Approval Needed | Carolyn Marquis | 2024-03-01 |  | Checking with Alfred on Tshirt price
4 | COA Approval Needed | Renata | 2024-03-01 |  | Lease extended through Septebmer 30, 2024
5
6
7
8
Legal Resources Management
1 | Magistrate Hearing 1 | Legal Committee | 2024-01-09 |  | 22Owners/71online - 30 days for trap bags and fence and fines will begin
2 | Magistrate Hearing 2 | Legal Committee | 2024-02-14 |  | H wants walk garage walkthrough, Magistrate finds H as owner; 30 days then fines
3 | Magistrate Hearing 3 | Legal Committee | 2024-03-01 |  | Hearing on Garage and Balconies
3 | Mediation #3 | Board | 2024-03-28 |  | Demonized NDA; nothing shared. Details worked next 30 days - Maybe share with owners?
4 | Magistrate Hearing 3 | Legal Committee | 2024-04-09 |  | Fines to H 1,000daily. Trap bags and fence order
5 | Mediation #4 | Board | 2024-04-11 |  | Details were to be worked out; by 4/22 nothing to share with owners
6 | Volusia Circuit Court Hearing on 14th Floor | Joel Attorney | 2024-04-23
7 | Magistrate Hearing 4 | Legal Committee | 2024-06-05
8 | Arbitration????
9
10
11
Bylaws Review
1 | Coordination Needed | Review Committee
2 | Committees Solicited | Review Committee
3
4
5
INSURANCE |  |  |  |  | Present and Next Steps
1 | Insurance Needed | Hire the Insurance Adjuster Attorney for COA | 2023-01-05 |  | Board has refused to hire expert
2 | Referred to Legal for recommendation | COA Attorney | 2023-01-11 |  | Board continues to do nothing on Insurance
3 | COA Approval Needed | Nathan Wade | 2023-02-12 |  | Nothing being done by Board
4
5
6
7 | Governmental Expertise Needed | Volusia County | 2024-05-22 | 2024-03-23 | Get Clarification |  |  |  | Yes
[5 empty] | TOTALS | 3269600 | 1307150

## Pots$$$
POTS OF MONEY $$$
Description | Where is it now? | amount? | Where should it be? | SOLUTION
$38,000 insurance reimbursement from storm | Developer | 38000 | Insurance Trustee Account | Hire Insurance Adjuster Attorney for investigation
Utilities Deposit by COA | Developers Name | 60000 | COA Reserves | File for account change
EBITDA 10% Award 2019 (SOL 2025) | Developers Records | 1500000 | COA Reserves | File to Enforce Award
160,000 Required by Develper | Developer | 160000 | UBS Reserve Account | File for UBS Account funds
True Up 2 Million | Developer | 2000000 | Forensic Account Account | File for Arbitration to Resume
14th Floor Unpaid Monthly Assessments for 2-3 years | Developer/Court | 1500000 | COA Assessment Account | File each lien with Airbnb and VRBO so rental fees come to COA ACCOUNT
Lost Rental Revenue and Devaluation of DBR | COA | 7000000 | COA Owners Account | Class Action Tortious Interference Claim on behalf of DBR Owners
| TOTAL OWED TO OWNERS AT DBR | 12258000
| Estimate Legal fees to collect | 700000

## Floor Capt
FLOOR AT DBR | NAMES | NUMBER
1 | Carolyn and David Marquis | 240 298-1195
2
3 | Mary and Larry Thurman | 386 301-0963
4 | Karen Fanning | 52 296-4636
5 | Ricky and Susan
6 | Linda Turkowski | 608 931-9486
7 | Roger and Martha Kubly | 608 628-2068
8
9
10 | Jill and Joe | 386 843-3194
11
12 | Vita and Allen
13
14
Kimberly Thomplison |  | 386 463-0204
Tomoka Property |  | 386 387-2010
Security

## Resource
Resource Needed
Click on the Resources description to update the project plant for the Description type and hit 'enter'
Resources Needed
COA Approval Needed
DBR LLC Approval Needed
Vendor Quotes Needed
Tomoka Resources Needed
Insurance Needed
Coordination Needed
Funding Needed
Waiting on Parts and/or Estimates from Vendor
Referred to Legal for recommendation
Law Enforcement Needed
Governmental Expertise Needed
Social Activity Needed
Other Needed